## TMS-Portal (hidden)
Sno | Login Type | Module | Priority | Status | Remarks | Web | API | API Timeline
1 | Transporter | Transporter Dashboard | 2 | Bug |  | Mehdi | Mustaqeem
2 | Transporter | TMS Dashboard | 2 | Closed |  | Saumya | Deepak
3 | Transporter | Billing | 1 | Closed |  | Mehdi | Deepak | 2025-03-02
4 | Transporter | Agreement | 1 | Closed |  | Saumya | Deepak | 2025-03-02
5 | Transporter | Vehicle Dashboard | 1 | Closed |  | Mehdi | Mustaqeem | 2025-02-28
6 | Transporter | Driver Dashboard | 1 | Closed |  | Mehdi | Mustaqeem | 2025-03-04
7 | Transporter | Document Wallet | 1 | Closed |  | Saumya | Mustaqeem | 2025-03-04
9 | Customer | Customer Dashboard (Summary Dashboard) | 1 | Done |  | Saumya | Mayank | Done
10 | Customer | TMS Dashboard | 2 | Closed |  | Saumya | Deepak
11 | Customer | Billing | 1 | Closed |  | Mehdi | Deepak | 2025-03-02
12 | Customer | Agreement | 1 | Closed |  | Saumya | Deepak | 2025-03-02
13 | Customer | Vehicle | 1 | Closed |  | Mehdi | Mustaqeem | 2025-02-28
14 | Customer | Driver | 1 | Closed |  | Mehdi | Mustaqeem | 2025-03-04
15 | Customer | Document Wallet | 1 | Closed |  | Saumya | Mustaqeem | 2025-03-04
16 | Customer | Trip Dashboard | 1 | Closed |  | Mehdi | Mayank | Done
17 | Transporter | Transporter Module external | 1 | Closed |  | Mehdi
18 | Transporter | Fleet Performance Report |  | Closed
19 | Transporter | Distance Report |  | Closed
20 | Transporter | Monthly report |  | Closed
21 | Transporter | Travelle Report |  | Closed
22 | Transporter | Load Planner |  | TBD
23 | Customer | Route Planner |  | TBD

## BDE (hidden)
Page | Layout Owner | API Owner | Layout Status | API Status | Status | Timeline
Trip Dashboard | Mehdi | Mayank | Done | Done | Done | 2025-02-05
IRUN | Saumya | Mayank | Done | Done | Done
Slot wise report | Mehdi | Mayank | Done | Done | Done
Delay Dashboard | Saumya | Mayank | Done | Done | Done | 2025-02-05
Summary Dashboard | Saumya | Mayank | Done | Done | Done | 2024-02-06
Data Push Report | Saumya | Mayank | Done | Done | Pending
Network Delay report | Saumya | Mayank | Done | Done | Done
Vehicle Utilization | Saumya | Mustaqeem | Done | Done | Closed | 2024-02-07
Trip Report | Saumya | Mayank | Done | Done | Done | 2024-02-08
Vehicle Report | Saumya | Mayank | Done | Done | Done
Vehicle Nearby | Saumya | Mayank | To be move to prod | To be move to prod | Done | 2025-02-05
Delay Report | Saumya | Mustaqeem | 2024-02-10 | Done | Done
Script for slot wise report for trip details |  | Mayank | NA | 2024-02-10 | Pending
Home Vehicle | Saumya | Mayank/Alam | 2025-02-11 | 2025-02-11 | Done | 2025-02-05
Region , Transporter and Manager type login | mehdi | Taseen Sir | NA | done | Done | 2025-03-27

## TMS@New API List
Page | API Name | urls | payload | response
Profile | profile-picture | https://apinode1.secutrak.in/mobileApiRetail/profile-picture | AccessToken:71l15yvWYjx9rgZB03600iF30Rn77Q60 file:
| change password | https://apinode1.secutrak.in/dev-app-secutrak/changePassword | AccessToken: current_password: new_password: repeat_new:
| loginV3 | https://apinode2.secutrak.in/dev-app-itraceit/loginV3 | GroupId,UserId,Password
| View Profile | https://apinode2.secutrak.in/dev-app-cvmanage/getProfileInformation | AccessToken:
| Edit Profile for company info | https://apinode2.secutrak.in/dev-app-cvmanage/updateProfileInformation | AccessToken gst_no:TEST123 company_name:Mohd Mustaqeem Ansari com_address:kanpur pan_no:ABC1234CDE45 tin_no:MDMUSTAQEEM123 form_type id
| Edit Profile for company info | https://apinode2.secutrak.in/dev-app-cvmanage/updateProfileInformation | gst_no:TEST123 first_name:Mohd Mustaqeem Ansari last_name: con_address:kanpur email:test@test.com contact_no:4444 id:108 form_type:contact_info
| List Branch | https://apinode2.secutrak.in/dev-app-cvmanage/listUserBranch | AccessToken
| Add Branch | https://apinode2.secutrak.in/dev-app-cvmanage/addUserBranch | AccessToken:10nF30c8BWk9YP1H78rQ168yRNLf4001 transporterId:86194 * email:test@ingen.com contact_no:995506344600 branchname:ITS code:ITS123 state:Uttarpradesh city:Kanpur address:Rawatpur representative:ITS gstinno:123456789123456 geocoord:82.679,24.3345 | * optional
| Edit Branch | https://apinode2.secutrak.in/dev-app-cvmanageeditUserBranch | AccessToken:10nF30c8BWk9YP1H78rQ168yRNLf4001 transporterId:86194* email:test@ingen.com contact_no:995506344600 branchname:ITS code:ITS123 state:Uttarpradesh city:Kanpur address:Rawatpur representative:ITS gstinno:123456789123456 geocoord:82.679,24.3345 id:1

## CV 18 Bug point
SN | Point | Page | Status | Bug Raise Date | Timeline
1 | Side menu look and feel not good | Irun | Closed | 2026-04-01
2 | Page is loding slow | Irun | Closed | 2026-04-01
3 | Add loader image | Irun | Closed | 2026-04-01
4 | Pie chare hide /unhide option is not working | Irun | Closed | 2026-04-01
5 | feature name should be displayed on icon mouse over | Irun | Closed | 2026-04-01
6 | While clicking on the High Value Toggle Switch, an alert pop-up message is showing | Irun | Closed | 2026-04-01
7 | Pie chart filter is not working or Display incorrcet Data | Irun | Closed | 2026-04-01
8 | Alert History are showing incorrcet | Irun | testing pending | 2026-04-01
9 | Route, Source , Destination , colour Shipment method filter is not working | Irun | Closed | 2026-04-01
10 | While clicking on the tracking map, it loads slowly, or sometimes the map does not load at all. | Irun | Closed | 2026-04-01
11 | whicle click on tracking bubble need to GPS service provider | Irun | New requiremet | 2026-04-01
12 | whicle click on tracking bubble need to lock Status (open/Closed) | Irun | New requiremet | 2026-04-01
13 | Vehicle stop time are not Showin in some trips | Irun | Closed | 2026-04-01
14 | One Alert are showing many time in above menu filter | Irun | Closed | 2026-04-01
15 | Vehicle is running but vehicle status are showing Stop | Irun | Closed | 2026-04-01
16 | While downloading the CSV report, the locked column value shows a name instead of being blank. | Irun | testing pending | 2026-04-01
17 | Unable to download trigger report | Irun | testing pending | 2026-04-01
18 | Max Speed should be display up to two digit | Irun | Closed | 2026-04-01
19 | While clicking on a threat, some other options are not showing in the filter. | Irun | testing pending | 2026-04-01
20 | Add Map icon in report | Lock report | New requiremet | 2026-04-01
21 | Add Device type filter | Lock report | New requiremet | 2026-04-01
22 | Add Device imei filter | Lock report | New requiremet | 2026-04-01
23 | vehicle no _VE_860181061720808 not showing in lock report | Lock report | Bug | 2026-04-01
24 | Once we mention remarks during closed the alert at same time portal is working slow | Irun | Bug | 2026-04-01
25 | QRT user should not be display while cloase the alert if QRT not assign | Irun | Bug | 2026-04-01
26 | Unable to close alert ( page Re-direct on previus page ) | Irun | Closed | 2026-04-01
27 | Route type Filter not working | Trip Dashoard | Bug | 2026-04-01
28 | While Apply the (JDH to AMG) Source and Destination filter pop-up Display Should be display (if no data Available ) | Trip Dashoard | Bug | 2026-04-01
29 | After Complete the trip all Action button should be Disable Except Edit trip | Trip Dashoard | Closed | 2026-04-01
30 | vehicle is running but allaction button are disable insteat of Enable | Trip Dashoard | Bug | 2026-04-09
31 | Tracking link generate but not working | Trip Dashoard | Bug | 2026-04-01
32 | A camera icon should be displayed for a trip if a dashcam is installed. | Trip Dashoard | Bug | 2026-04-09
33 | Elock Statu are showing blanck in table (trip id : 11266937) | Trip Dashoard | Bug | 2026-04-01
34 | Add eLock status (Open/Closed) when we click on Tracking Bubbles. | Trip Dashoard | Bug | 2026-04-01
35 | feature name should be displayed on icon mouse over | Trip Dashoard | Closed | 2026-04-01
36 | Play Track in not availabe | Trip Dashoard | Closed | 2026-04-01
37 | Live Tracking stop/play botton is not Available | Trip Dashoard | Closed | 2026-04-01
38 | Googgle map Size is too large while click on tacking | Trip Dashoard | Closed | 2026-04-01
39 | Pic chart Filter is not working | Trip Dashoard | Bug | 2026-04-01
40 | Vehicle last time should be Blank insteat of NA | Trip Dashoard | Closed | 2026-04-01
41 | Driver no are showing in incorrcet Format | Trip Dashoard | Closed | 2026-04-01
42 | users Can Cancel the trip maximum duration of 6 hours.(Configrable) | Trip Dashoard | New requiremet | 2026-04-01
43 | Add Trip Cancellation Reason (Incorrect vehicle number,(i)Incorrect route code,(ii) Incorrect run code,(iii) Incorrect flight number,(iv) Trips not closed at the destination | Trip Dashoard | New requiremet | 2026-04-01
44 | While editing, the driver name should not be accepted in numeric form, and the driver ID should be accepted in numeric form only.( no Should be minimun 10 Digit) | Trip Dashoard | Closed | 2026-04-01
45 |  |  |  | 2026-04-01
46 | Api is working Slow | Trip Dashoard | Bug | 2026-04-01
47 | Unable to drag Google Map -pop-up | Trip Dashoard | Bug | 2026-04-01
48 | If session timeout, no msg displayed during the search or selection | Slotwise Distance Report | Bug | 2026-03-19
49 | No typed text is visible after first selection in Vehicle box | Slotwise Distance Report | Bug | 2026-03-19
50 | Datagap Standing column need to add in detailed report under + icon (Only in Master login) | Slotwise Distance Report | Bug | 2026-03-19
51 | The Exception Date selection does not influence the generated report. | Slotwise Distance Report | Bug | 2026-03-19
52 | Vehicle selection in Agreement based report does not influence the generated report | Slotwise Distance Report | Bug | 2026-03-19
53 | Wrong STA displayed in Trip closed window | Trip Dashboard | Bug | 2026-03-23
54 | ATA Should not be selected for future dates & before run date | Trip Dashboard | Bug | 2026-03-23
55 | Failed to download report of one whole month | Trip Report | Bug | 2026-03-30
56 | Timeline not available under track of trip report | Trip Report | Bug | 2026-03-30
57 | Mouseover display required in hidden text | Trip Report | Bug | 2026-03-30
58 | Trips rundate 01-01-2026 00:00:00 are skipping in generated report at the filter applied from date 01-01-2026 onwards. | Trip Report | Bug | 2026-03-30
61 | Valued not available in Column "Delay arrival". | Trip Report | Bug | 2026-03-30
| 10912911, 900001043298040, 10959827 |  | Bug
62 | Valued not available in Column "Delay TT". | Trip Report | Bug | 2026-03-30
| 900001044258184, 900001043729345, 900001044066669, 900001043048367, 900001043439381, 10889910, 900001042685218 |  | Bug

## Node App
SN | Point | Account | Owner | Bug | Status | Date | Timeline
1 | Unable to track vehicle in trip dashboard | Bluedart Node App | Deepankar | Closed | Done | 2025-10-01
2 | trip Location in/out time is not showing | Bluedart Node App | Deepankar | Closed | Done | 2025-10-01
3 | Trip Complete/Schedule filter is not working. | Bluedart Node App | Deepankar | Bug | Done | 2025-10-01
4 | Vehicle last location page tab is not working. | Bluedart Node App | Deepankar | Bug | Done | 2025-10-01
5 | While creating the trip, getting error "Error" | Bluedart Node App | Deepankar | Bug | Closed | 2025-10-01
6 | When creating the trip, a network error occurs once we enter the driver's mobile number. | Bluedart Node App | Deepankar | Closed | Done | 2025-10-01
7 | Google Maps is not loading on the live vehicle menu. | Bluedart Node App | Deepankar | Bug | Pending | 2025-10-01
8 | When clicking on text mode, the page switches to map mode in the live vehicle menu. | Bluedart Node App | Deepankar | Closed | Done | 2025-10-01
9 | Google Maps is not loading while tracking the vehicle in the Track Vehicle menu. | Bluedart Node App | Deepankar | Bug | Done | 2025-10-01
10 | Some Trip are not showing (10208682) | Bluedart Node App | Deepankar | Bug | Done | 2025-10-09
11 | App is working slow | Bluedart Node App | Deepankar | Bug | Pending | 2025-10-09
12 | once we selcet the portable device app is only processing | Bluedart Node App | Deepankar | Bug | Done | 2025-10-23
12 | Schedule departure time is not fecting automatic | Bluedart Node App | Deepankar | Bug | Done | 2025-10-23
12 | Same Vehcile trip is createing | Bluedart Node App | Deepankar | Bug | Pending | 2026-02-02
12 | Unable to cancelled trip ( Display Network error) | Bluedart Node App | Deepankar | Bug | Pending | 2026-02-11
12 | once we select location while creating the the polygon lat-long should be auto capture and google map size need to be increase.
12
12
12

## TMS@New
SN | Page | Point | Remarks | Sequence | Web Timeline | Layout Owner | API & Backend Owner | Layout Status | API Timeline | APIStatus | GUI Owner | TimelineGUI | GUIStatus | Final Status | Remarks
1 | TMS | Registration CorporateTransporter |  | 2 | 2025-09-24 | Himanshu | Mustaqeem | Provided | 2025-08-07 | Done | Mehdi | 2025-10-06 | Share | Done
2 | TMS | Profile and Location KYC |  | 1 | 2025-09-24 | Himanshu | Mustaqeem/Taseen | Provided | 2025-08-06 | Done | Mehdi | 2025-08-09 | Share | Done
3 | TMS | Customer Transporter Branch Mapping | (assign code) | 2 | 2025-09-24 | Himanshu | Mustaqeem/Taseen |  | 2025-08-08 | Done | Mehdi | 2025-10-06 | Share | Done | doc share pending
4 | Route Fleet | Route Fleet |  | 1 | 2025-09-24 | Himanshu | Mustaqeem/Taseen | Provided | 2025-08-08 | done | Saumya | 2025-08-12 | Share | Done | doc sharing pending
5 | CCE | CCH Dashboard |  | 4 |  | Himanshu | Mustaqeem | Done | 2025-09-10 | pending | Sanvi | 2025-10-28 |  | Done
6 |  | Invoicing | Assign State, Region | 2 |  | Himanshu | Deepak | Pending | 2025-08-08 | Pending | Saumya | 2025-08-13 | Pending | Done | Changes discussed 03-09-2025 in API logic
7 |  | Agreement | Assign State, Region | 2 | 2025-09-24 | HImanshu | Deepak | Pending | 2025-08-08 | pending | Saumay | 2025-08-13 | Pending | Done | Changes discussed 03-09-2025 in API logic
8 | CCE | Login Mapping | Assign State, Region to Login user | 3 | 2025-09-01 | Himanshu | Mayank | Pending | 2025-08-11 | pending | Mehdi | 2025-08-13 | Pending | Done | User details Share on 5th Feb
9 | CCE | Call Center Assginment |  | 4 |  | Himanshu | Mustaqeem | Done | 2025-09-10 | Done | Sanvi | 2025-10-28 |  | Done | Done
10 | CCE | Manage Shift |  | 4 |  | Himanshu | Mustaqeem | Done | 2025-09-10 | Done | Sanvi | 2025-09-15 |  | Done | Done
11 | CCE | CCO Dashboard |  | 4 |  | Himanshu | Mustaqeem | Done | 2025-09-10 | pending | Sanvi | 2025-10-28 |  | Done
12 | CCE | CCTL Dashboard |  | 4 |  | Himanshu | Mustaqeem | Done | 2025-09-10 | pending | Sanvi | 2025-10-28 |  | Done
13 | CCE | CCTL Performance Dashboard |  | 4 |  | Himanshu | Mustaqeem | Done | 2025-09-10 | pending | Sanvi | 2025-10-28 |  | Done
14 | CCE | CCH Performance Dashboard |  | 4 |  | Himanshu | Mustaqeem | Done | 2025-09-10 | pending | Sanvi | 2025-10-28 |  | Done
15 | CCE | Employee Performace report | [7 empty] | pending | Sanvi | 2025-10-30 |  | Done
16 | CCE | Call Center Attendance ( Roaster) |  | 4 |  | Himanshu | Mustaqeem | Done | 2025-09-10 | pending | Sanvi | 2025-10-28 |  | Done | Done
17 | Home Vehicle | Home vehicle filters: Make & Model, GPS Vendor. |  | 5 | [6 empty] | Saumya |  |  | Done
18 | Home Vehicle Live | Speed to be added in vehicle listing. | [8 empty] | Saumya |  |  | Done | Can this be seen over mousever, as listing will take more space.
19 | CCE | TL Critical Escalation Report |  | 4 |  | Himanshu | Mustaqeem | 2025-09-10 | pending | pending | Sanvi | 2025-10-30 |  | Done
20 | TMS | Register trasnporte should be reflect in Customer login | [8 empty] | Mehdi |  |  | Pending
21 | TMS | Add option in Trasnporte master login assign vehicle to customer | [8 empty] | Mehdi |  |  | Pending
22 | Vehicle dashboard | vehicle KYC |  | 4 |  | Himanshu | Deepak | 2025-08-29 |  |  | Mehdi |  |  | Pending | ILGIC CV PPT : Page No: 2 & 3
23 | Driver dashboard | driver KYC |  | 4 |  | Himanshu | Deepak | 2025-08-29 |  |  | Mehdi |  |  | Pending | ILGIC CV PPT : Page No: 4 & 5
24 | GST | GST Integration |  | 5 |  |  | Deepak |  |  |  | Mehdi |  |  | Pending | API pending from Operation
25 | MigrationWork | RouteFleetMigrationWork | scrpit,mobileapi,others,db | 5 |  | NA | Taseen/Mustaqeem/Arpit/Mayank |  | 2025-09-12 | NA | Saumya/Mehdi |  |  | Pending
26 | MigrationWork | TransporterMigrationWork |  | 5 |  | NA | Taseen/Mustaqeem/Arpit/Mayank |  | 2025-09-12 | NA | Saumya/Mehdi |  |  | Pending
27 |  | Mapping of vehicle with Insurer |  | 3 | Done | [8 empty] | Done
28 | Master cv | Consolidated Dashboard: Two Filters 1. groups 2. CV and others |  | 3 | 2025-08-29 |  | Mustaqeem/Mayank | [6 empty] | Done
29 | TMS | Consolidated Dashboard: Risk Score |  | 4 | [9 empty] | Done
30 | MigrationWork | Angular 18 Migration |  | 5 | Share plan |  | Mustaqeem |  | 2025-09-12 | NA | Saumya/Mehdi |  |  | Pending
31 | Irun | Need to add drop down list while close the alert (Irun) |  | 4 | Done | Himanshu | Saumya | Share | [5 empty] | Done | layout missing
32 | Slot Wise | Need to be add day wise direct Download with all details. Like data gap and Working hours (Slot wise ) |  | 4 |  | Himanshu | Taseen Sir | Share |  |  | Mehdi | 2025-09-05 |  | Done | 2025-09-05
33 | TMS Customer | CV Risk Score |  | 4 |  |  | Rizwan |  |  |  |  | 2025-10-28 |  | Done
34 | IRUN | If Any Alert bucket is 0 , Then Color of Chart should be of single color(Green). |  |  |  |  | Saumya |  |  |  | Saumya |  |  | Done
35 | TMS Customer Login | Require upload doucment option and view doucument |  | 4 | [6 empty] | Saumya |  |  | Done
36 | Irun | Tracking Option in Trip Dashboard, IRUN along with live tracking. ( Simillar to PDS) |  | 1 | [9 empty] | Done
37 | Irun | Jump in Live Tracking Option and play track option similar to retail dashboard. Vehicle Ball icon to be replaced with vehicle icon. |  | 1 | [6 empty] | Saumya |  |  | Done
38 | Trip report & home Vehicle | Line chart summary in trip report similar to Fleetx |  | 1 | [6 empty] | Saumya |  |  | Done
39 | All Pages | Customer Location address should be displayed if vehicle lies wihtin 1 km geofence. |  | 2 | [6 empty] | Saumya | 2025-10-17 |  | Done
40 | Irun | Google Map to be fitted in a single page. Remove horizontal scroller |  | 2 | [9 empty] | Done
41 | Irun | Speed baloon filter to be placed in right bottom corner without any heading. On click of a filter, baloon in map should be show/hide. |  | 3 | [9 empty] | Done
42 | Home page | Need filters in map for Stoppage, Arrow, Direction. Reduce arrow count. |  | 3 | [6 empty] | Saumya |  |  | Done
43 | Home page | Home vehicle page loading too slowly. Google landmarks are not displaying.( Added in dairy recently) |  | 3 | [6 empty] | Saumya |  |  | Done
44 | Report | Halt report to be added in BDE. Also, need to shift address in last column with shorten details and show in mouse hover and replace lat long with Map view button and timelines in every report. |  | 2 | [6 empty] | Taseen Sir/ Saumya |  |  | Done
45 | Irun | Calender Should be changed in all reports and dashboards. |  | 5 | [9 empty] | Done
46 | IRUN | Provision to mark a vehicle as Off-Road Vehicles after that no alert is generated untill the vehicle revoked from Off-road. A summary need to be shown as shared. |  | 2 | [6 empty] | Saumya | 2025-10-30 |  | Done | ILGIC CV PPT : Page No: 9, Layour need to be revised. Bar chart rewuired instead of multiple pie chart.
47 | IRUN | Critical Alert Icon in IRUN Dashboard to be changed. | [11 empty] | Done
48 | IRUN | All pie chart color become green when count is zero | [11 empty] | Done
49 | IRUN | Repetative alert in case of vehicle standing at same place for more then 30 Minutes in critical alert and for remaining 45 Minutes after the alert closure. | [11 empty] | Done
50 | DHL | Add Trip creation Page | [8 empty] | Mehdi |  |  | Done
51 | Bluedart | Intercity trip API creation modification (backend) | [11 empty] | Done
52 | Home Vehicle | Play Track option with halt flags with speed increase and decrease option. Replace the Ball icon with the vehicle icon. | [11 empty] | Done
53 | VAPT point | New VA & AA ( VAPT point) | [11 empty] | Pending
54 | Home Vehicle | ILGIC CV Home Vehicle Page improvision. | [11 empty] | Hold | ILGIC CV PPT : Page No:10,11, and 12.
55 | IRUN | Scheduled Halt(also called Sector Delay-Touchpoint Alert) Where User will update Remarks using below filter: 1. Less Load 2. Labour Issue 3. Space Constraint 4. Driver Not available 5. Document issue 6. Others |  | 2 | [6 empty] | Saumya | 2025-10-29 |  | Done | Mail Communication Attached
56 | Trigger Report | Route Type Filter Required | [11 empty] | Done
57 | IRUN | Open Delay reason need to be added in IRUN dashboard in a separate column |  | 1 | [6 empty] | Saumya |  |  | Done
58 | IRUN | check box to be given to remove Grace alerts from display. |  | 1 | [6 empty] | Saumya |  |  | Done
59 | IRUN | Location & history To shifted on Left hand side after Column vehicle column. Address should be word wrap and on tool tip/download it should display entire address |  | 1 | [6 empty] | Saumya |  |  | Done
60 | IRUN | IRUN Sirun should be activated after 30 seconds from login. |  | 1 | [6 empty] | Saumya |  |  | Done
61 | IRUN | IRUN tracking page, on click of alert icon alert details should be diplayed as Alert Name, Start Time, and End time. |  | 1 | [6 empty] | Saumya |  |  | Done
62 | Nearby Dashboard | when user search nearby with respect to a vehicle then in map base vehicle should be appear as Pointer. On click it shows the vehicle details. | [8 empty] | Mehdi | 2025-10-31 |  | Done
63 | Nearby Dashboard | For every nearby search, all BDE location should appear that exist within 100Km radius or all. | [8 empty] | Mehdi | 2025-10-31 |  | Done
64 | Trip Dashboard | Option to Show/Hide any pie chart ( Simillar to IRUN). Vehicle Status in Pie chart to be rename as GPS Status. |  | 1 |  |  | Taseen |  | 2025-10-31 |  | Mehdi | 2025-10-31 |  | Done | ILGIC CV PPT : Page No: 6,7,and 8
65 | Trip Dashboard | 2 new pie chart to added as "Departure" and "E-Lock Status". Need to remove stopage alert pie chart. Table content has to chnaged accordingly. |  | 1 |  |  | Mayank/Taseen |  | 2025-10-31 |  | Mehdi | 2025-10-31 |  | Done | ILGIC CV PPT : Page No: 6,7,and 8
66 | Profile (Transporter Branc Assigment ) | Add Branch field Contact Details whiile assign the branch |  |  | 2025-09-26 | [8 empty] | Done
67 | Bluedart | Add Play track option in irun dashboard & trip dashboard similar to PDS paddy |  |  | 2025-10-03 | [8 empty] | Done
68 | Bluedart | Add alert flag in trip report |  |  | 2025-10-03 | [8 empty] | Done
69 | Consolidated Dashboard | ILGIC CV Consolidated dashboard improvision. | Trip Dashboard | [10 empty] | Hold | ILGIC CV PPT : Page No:13,14, and 15.
70 | Bluedat | Display polygon (if Available) in trip report/dashboard/ Irun dashboard insteat of Radius |  | 5 |  |  | Taseen Sir/ Saumya |  |  | Pending | Saumya |  |  | Done | trip dashboard is completed
71 | Trip Report | Add new column Portable Device Number (IMEI) |  | 1 | [6 empty] | Saumya |  |  | Done
72 | Trip Report | Trip Report, user can choose feeder type without selecting the run type. |  | 1 | [6 empty] | Saumya |  |  | Done
73 | Bluedart | All delayed remarks only as per the GNMS sequence require in Delay Dashboard |  |  |  |  | Mayank |  |  |  | NA |  |  | Done
74 | Delay Dashboard | Add Coloum ,Flight Number , Live remarks option ,ETD( KM ) & TOTAL DISTANCE | [8 empty] | Saumya |  |  | Done | only Live Remarks Option is pending
75 | Trip Dashboard | Add new column Portable Device Number (IMEI) |  | 1 |  |  |  |  | 2025-10-31 |  | Mehdi | 2025-10-31 |  | Done
76 | Trip Dashboard | Change Sch_halt logic |  | 1 |  |  | Mayank |  | 2025-10-30 |  | NA |  |  | Done
77 | Report | Lock report in DHL Account | [8 empty] | Saumya | 2025-11-10 |  | Done
78 | Delay Dashboard (DHL & Xiomi) | Add trip id coloum in Irun dashboard | [8 empty] | Saumya |  |  | Done
79 | Root admin | Root Admin all Pages |  | 5 |  | Himanshu |  | 2025-08-31 | [5 empty] | Pending from Ops Team
80 | Route Schedular | Route Schedular |  | 2 | ?? | Himanshu | Maynak | 2025-08-30 | 2025-08-11 | pending | Mehdi | 2025-10-28 | Pending | Done | layout share on 5th Sep
81 | Sepio ( RFID) | Customer Profile |  |  | 2026-02-04 | Himanshu | Taseen, Mustaqeem |  |  |  | Mehdi |  |  | Done | Sepio PPT : Page No: 13 & 14
82 | Sepio ( RFID) | Data Validation ( Excel Attached) | [11 empty] | Done | Excel attached (ICICI_validation_Fields)
83 | DHL | DHL Fleetx Api Integration | [9 empty] | 2025-11-14 |  | Done | ApI Share to arpit
84 | Bluedart | add poratle Device no Coloum Same as trip report | [11 empty] | Done
85 | DHL & Xiomi | Add Battery % Menu to monitor Portable Device & Portable E-lock Batter | [8 empty] | Saumya |  |  | Hold
86 | Bluedart | All the alerts that are supposed to generate inside the BDE location, like Delay Departure, Sector Delay, Sch_halt Alert, Location Name and STD details, are to be added. | [8 empty] | Saumya |  |  | Done
87 | Bluedart | Breakdown Start time and a manual option to enter need to be added to the Off-Road pop-up page. Also, need to provide an option to upload a document and an image. | [8 empty] | Saumya |  |  | Done
88 | Bluedart | To mark a vehicle as off-road should be available only in the customer login. | [8 empty] | Saumya |  |  | Done
89 | Bluedart | Add one new filter of trip ID. In Trip dashboard | [8 empty] | Mehdi |  |  | Done
90 | Bluedart | In every summary pie chart, the centre total count should be clickable, and the respective trip should be visible only in the table. | [8 empty] | Saumya |  |  | Done
91 | Bluedart | Add Fixed GPS Exception, Fixed Elock Exception & Portable Elock Exception in trip report (select multiple exception types at once.) | [8 empty] | Saumya |  |  | Done
92 | Bluedart | If the vehicle is off-road, alert will be generated after 6 hours, except for lock alerts. | [8 empty] | Mayank |  |  | Hold
93 | Bluedart | Add GPSFixed GPS Exception, GPS Exception 2 in trip report (select multiple exception types at once.) | [8 empty] | Saumya |  |  | Done
94 | Bluedart | Fix GPS pie chart: Remove Stopped and Running. Add the two with name "Active | [8 empty] | Saumya |  |  | Done
95 | Bluedart | Fix Elock pie chart: Remove Stopped and Running. Add the two with name "Active" | [8 empty] | Mehdi |  |  | Done
96 | Bluedart | RNCC Login: | [11 empty] | Done
97 | Bluedart | Require address in Slot wiser report |  |  | 2025-12-28 |  |  |  |  | Done | Mehdi |  |  | done
98 | Sepio ( RFID) | Customer OnBoarding |  |  | 2026-02-04 | Himanshu | Taseen, Mustaqeem |  |  |  | Mehdi |  |  | Done
99 | Sepio ( RFID) | Manage Seal Customer for Registration |  |  | 2026-02-05 | Himanshu | Taseen, Mustaqeem |  |  |  | Mehdi |  |  | Done
100 | Sepio ( RFID) | Manage Product |  |  | 2026-02-06 | Himanshu | Taseen, Mustaqeem |  |  |  | Mehdi |  |  | Done
101 | Sepio ( RFID) | Manage Conatainer |  |  | 2026-02-06 | Himanshu | Taseen, Mustaqeem |  |  |  | Mehdi |  |  | Pending
102 | Sepio ( RFID) | Manage Vassel |  |  | 2026-02-07 | Himanshu | Taseen, Mustaqeem |  |  |  | Mehdi |  |  | Pending
103 | Sepio ( RFID) | Company Registration by ICICI |  |  | 2026-02-05 | Himanshu | Taseen, Mustaqeem |  |  |  | Mehdi |  |  | Pending
104 | Sepio ( RFID) | Place Order |  |  | 2026-02-10 | Himanshu | Taseen, Mustaqeem |  |  |  | Mehdi |  |  | Done
105 | Sepio ( RFID) | Trip Creation |  |  | 2026-02-15 | Himanshu | Taseen, Mustaqeem |  |  |  | Mehdi |  |  | Pending | (TDB issue in Layout on different way of shipment and how to combine or track any conatiner upto destination)
106 | Sepio ( RFID) | Report |  |  | 2026-02-17 | Himanshu | Taseen, Mustaqeem |  |  |  | Mehdi |  |  | Pending
107 | Bluedart | Add Complain Module in Portal | [8 empty] | Mehdi |  |  | Pending from Ops Team | Layout Pending from ops team
108 | Bluedart | millitrack Api Integration | [8 empty] | Arpit |  |  | Done
109 | Bluedart | Portable Device tracking should be showing in Home page | [8 empty] | Saumya |  |  | Hold
110 | Bluedart | To mark a vehicle as a breakdown should be available in the BDE master login only. Need to remove from other logins. | [11 empty] | Done
111 | Bluedart | Realtrack API integration |  |  |  |  | Arpit |  |  |  | Arpit |  |  | Done
112 | Billing Module | Billing Module Modification |  |  |  |  | Deepak |  |  |  | Mehdi |  |  | Pending
113 | Bluedart | Pushing Cancelled Trip Data to BDE & Lynkit | [11 empty] | Done
114 | Bluedart | users Can Cancel the trip maximum duration of 6 hours. | [11 empty] | Done
115 | Bluedart | Trip Cancellation Reason (Incorrect vehicle number (i)Incorrect route code (ii) Incorrect run code (iii) Incorrect flight number (iv) Trips not closed at the destination | [11 empty] | Done
116 | Bluedart | Generate Trip API modifications to enable marking a trip as a critical shipment. | [11 empty] | Done
117 | Bluedart | Letsgro_Bluedart Pull Data Api integration | [11 empty] | Done
118 | LSP | Account Creation | [11 empty] | Done
119 | LSP | Transporter-LSP Vehicle Assigement | [11 empty] | Done
120 | LSP | Transporter-LSP Assigement | [11 empty] | Done
121 | LSP | LSP Customert - Assigement | [11 empty] | Done
122 | LSP | LSP Vehicle to Customer |  |  | 2025-01-30 | [5 empty] | Mehdi |  |  | testing pending
123 | LSP | Node Login for LSP User and permission |  |  | 2025-01-28 | [5 empty] | Mehdi |  |  | testing pending
124 | LSP | Transporter-LSP Agreement |  |  | 2025-01-28 | [5 empty] | Mehdi |  |  | testing pending
125 | LSP | Transporter-LSP Billing |  |  | 2025-01-28 | [5 empty] | Mehdi |  |  | testing pending
126 | LSP | LSP- Customer Agreement |  |  | 2025-01-28 | [5 empty] | Mehdi |  |  | testing pending
127 | LSP | LSP- Customer Billing |  |  | 2025-01-28 | [5 empty] | Mehdi |  |  | testing pending
128 | Billing Module | add an option to deduct a certain amount at the time a bill is approved |  |  | 2026-02-17 |  | Deepak |  |  |  | Mehdi |  |  | Pending
129 | Bluedart | While creating trip there should be option to mark trip as high value /Electronic shipment | [8 empty] | Deepankar/ Taseen sir |  |  | Pending
130 | Bluedart | Poratble lock count symbol in Tamper lock if any | [11 empty] | Done
131 | Bluedart | Future date/time selection should be restricted when closing trips. ( App and web Both) | [8 empty] | Mehdi |  |  | Pending
132 | Bluedart | SFC Intra / Inter option required in NCC login | [8 empty] | Saumya |  |  | Pending
133 | Bluedart | India map view or vehicles | [8 empty] | Saumya/ taseen Sir |  |  | Pending
134 | Bluedart | Trip Closure/cancel/termination through TMS API: Need to provide an API to lynkit. | [8 empty] | Arpit |  |  | TBD
135 | Bluedart | Trip Remarks to be added in API 2 Push | [8 empty] | Arpit |  |  | TBD
136 | Bluedart | During trip creation need to add option to set high value shipment. | [8 empty] | Arpit |  |  | TBD
137 | Bluedart | Need to add satellite map view in irun dashboard. | [8 empty] | Saumya |  |  | Pending
138 |  | Assest management | [8 empty] | Mehdi |  |  | Done
139 | Bluedart | Add Lock report in Bluedart |  |  |  |  | Taseen sir |  |  |  | Mehdi |  |  | testing pending
140 | Bluedart | QRT Report |  |  |  |  | Taseen sir |  |  |  | Saumya |  |  | Pending
141 | Bluedart | Dashcam Page on home page | [11 empty] | Pending
142 | Bluedart | Dashcam Page Trip dashboard | [11 empty] | Done
143 | Bluedart | Dashcam Page Trip report | [11 empty] | Pending
144 | Bluedart | Dashcam Page Delay dashborad | [11 empty] | testing pending
145 | Bluedart | Dashcam Page itraceit App | [11 empty] | Pending
146 | Bluedart | Assest management Dashboard ( lock history on pop-up ) |  |  |  |  | Taseen sir |  |  |  | Mehdi |  |  | Pending | Layout share on 28th March
147 | Bluedart | Add Trip Cancelled date and time coloum in trip report | [11 empty] | Pending
148 | Bluedart | Vehicle Reporting Module : Need provision to add a vehicle outside the master. | [11 empty] | testing pending
149 | Bluedart | Vehicle Reporting Module : relaxation up to 3 HRS | [11 empty] | testing pending
150 | Bluedart | Vehicle Reporting Module : Report and Distance in Slot wise report | [11 empty] | Pending | layout pending from ops team
151 | Bluedart | once we select location while creating the the polygon lat-long should be auto capture and google map size need to be increase. | [11 empty] | Pending
152 | Bluedart | Dashcam backend :need to segrigate thedashcam Alert with GPS data Alert ( Critical Alert) | [11 empty] | TBD
153 | Bluedart | Dashcam Backend : Need to rename multiple vendor's alert name in a common name | [11 empty] | TBD
154 | Bluedart | download Slot wise bulk report with upload excel | [11 empty] | TBD
155 | Bluedart | Secutrak API to push the lynkit master data into our system | [11 empty] | Pending

## CV & Bluedart Bug
SN | Point | Page | Account | Owner | Status | Bug Raise Date | Timeline | Priority | Remarks
1 | BA Report distance issue | BA Report | BA Backend | RizwanSir | Pending | 2025-08-08
2 | Customer Filter is not working Properly | Dashboard | CV | Mehdi | Done | 2025-08-06
3 | Vehicle Report filter is not working properly | Dashboard | CV | Saumay | Done | 2025-08-06
4 | All state Travall is showing blank | Dashboard | CV | Mehdi | Done | 2025-07-20
5 | Duplicate data push on lynkit server | Backend | Bluedart | Rizwan Sir / Arpit | Done | 2025-08-07
6 | While click on Graph Chart Vehicle listing is not showing | Master cv Dashboard | CV | Mehdi/ Saumya | Done | 2025-08-07
7 | Not working any filter in CV Dashboard. | Master cv Dashboard | CV | Mehdi | Done | 2025-08-05
8 | Click on Graph bar Alert table is not display | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-06
9 | Last data and status in vehicle report. | CV Dashboard | CV | Saumya/ Mustakeen | Done | 2025-08-05
10 | Duplicate vehicles in ILGIC consolidated dashboard | CV Dashboard | CV | Saumya/ Mustakeen | Done | 2025-08-05
11 | if trip closed by web closed by user name not update | Trip report / Trip Dashboard | Bluedart | Saumya/Mehdi/ Mayank | Done | 2025-08-14
12 | Alert count is incorrcet in graph | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-06
13 | while closeting trip it's take approx. 90 Sec to 120Sec | Trip Dashboard | Bluedart | Mehdi | Done | 2025-08-21
14 | Transporter filter is not working | Vehicle Report | CV | Mustakeen / saumya | Done | 2025-08-21
15 | Unable to update Contact Information & Company Information | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-08-25
16 | Unable to update Branch Details | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-08-25
17 | Departure time not showing once we click on fleeet details | Route fleet performance | TMS | Saumya | Done | 2025-09-03
18 | Scorller button not working while edit the fleet | Route fleet performance | TMS | Saumya | Done | 2025-09-03
19 | After Approved need to add popup msg | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
20 | After approved case should be disable | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
21 | Auto user id password shoulld be in small letter | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
22 | New Tranporter profile detail are showing blank | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
23 | Side Menu is not vsible in Transporter Onboarding Dashboard | Transporter Onboarding Dashboard | TMS | Mehdi | Done | 2025-09-03
24 | Side Scoller bad is too availabe | Transporter Onboarding Dashboard | TMS | Mehdi | Done | 2025-09-03
25 | Transporter Self Registration alignment layout looking good | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
26 | No Need to require register 2 time register mobile no (Transporter Self Registration) | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
27 | Mobile no should not be accept less than 10 digit (Transporter Self Registration) | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
28 | Uploaded Doucment thourg mail link is not showing in coustomer account | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
29 | After Reject the tranporter , transporter list is not showing | Registration CorporateTransporter | TMS | mustrakeem/Mehdi | Done | 2025-09-03 |  | Api issue
30 | While submit the register link form pop-up Should be display | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
31 | Need to be add Remark row in table | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
32 | Status are showing in 1 in excel and csv insteat of Approvd or Reject | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
33 | User name Should be in small letter (Auto mail) | Registration CorporateTransporter | TMS | Mehdi | Done | 2025-09-03
34 | UNSCHEDULED_HALT, PRIO, CRITICAL,Sensative Graph is not showing | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-06
35 | Transporter Self registration alignment layout is not correct | Transporter login | TMS | Mehdi | Done | 2025-09-03
36 | While Update the password need to add hide button | Transporter login | TMS | Mehdi | Done | 2025-09-03
37 | Incorrcet State are showing while update the Brach | Transporter login | TMS | Mehdi | Done | 2025-09-03
38 | Side Scoller bad is not availabe | Transporter login | TMS | Mehdi | Done | 2025-09-08
39 | While Seach the transporter Getting msg Branch Mapping empaty | Transporter Branch Assignment | TMS | Mehdi | Done | 2025-09-08
40 | Table data is showing incorrcet. it should be display as per the alert assigment | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-06
41 | Route type coloum is missing | Route fleet Assigement | TMS | Mehdi | Done | 2025-09-08
42 | Arrival Time is not updated in final distination while update fleet time | Route fleet Assigement | TMS | Mehdi | Done | 2025-09-08
43 | While update the fleet time getting error msg (An error occurred while saving.) | Route fleet Assigement | TMS | Mehdi | Done | 2025-09-08
44 | Add total count in Table | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-06
45 | Add hyperlink on table data | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-06
46 | Trigger count is incorrcet | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-18
47 | Require curger on mouse over | CCO Dashboard | Bluedart |  | Done | 2025-11-07
48 | Require Table data on bar Graph | CCO Dashboard | Bluedart |  | Done | 2025-11-07
49 | Google map is not showing on mouseover | Halt Report | Bluedart | Saumay | Done | 2025-10-11
50 | Data is loading slow while click on table hyperlink | CCO Dashboard | Bluedart |  | Done | 2025-11-07
51 | Require curger on mouse over | Call Center Attendance ( Roaster) | Bluedart |  | Done | 2025-11-08
52 | Alert Flag should be show after close the alert in tracking | Irun | Bluedart | Saumya | Done | 2025-08-01
53 | As per the home page vehile is stopped but in irun dashboard and trip dashboard it's showing running | Live Tracking | Bluedart | Mustakeen / saumya | Done | 2025-09-11
54 | Only Network data gap will be visible in Region type & Transporter type Account | Slot wise | Bluedart | Mehdi | Done | 2025-09-08
55 | Standing data gap is not showing while checking day wise report in master account | Slot wise | Bluedart | Mehdi | Done | 2025-09-08
56 | If vehicle assign with root admin the entry are showing in region login | Slot wise | Bluedart | Mehdi | Done | 2025-09-25
57 | Master CV account Card grap alignment not looking good | Dashboard | CV | Mehdi | Done | 2025-07-20
58 | Data range must be past date | CCH Dashboard | Bluedart | Sanvi | Done | 2025-10-22
59 | Vehicle is active but show inactive on irun dasboard | Irun | DHL | Mehdi | Done | 2025-09-27 |  | 1
60 | Last location and Speed are showing blanck | Irun | DHL | Mehdi | Done | 2025-09-27 |  | 1
61 | Current Data is available but vehicle status is showing Inactive | Trip dashboard | DHL | Mayank /Mehdi | Done | 2025-09-25 |  | 1
62 | There is no option to show to close alert | Trip Dashboard | DHL | Saumya | Done | 2025-09-25 |  | 1
63 | CCTL Performance Dashboard page is not working | CCTL Performance Dashboard | Bluedart | Sanvi | Done | 2025-10-18
64 | Need to add new update home page | Home Page | DHL | Saumya | Done | 2025-09-25 |  | 1
65 | Profile pic update but not showing | Profile | DHL | Mehdi | Done | 2025-09-25 |  | 1
66 | Unable to close trip because Customer location is not showing | Trip dashboard | DHL | Mehdi | Done | 2025-09-25 |  | 1
67 | Need to be remove Consolidated dashboard menu from master account | Consolidated dashboard | DHL | Taseen Sir | Done | 2025-09-25 |  | 1
68 | Remame TMS Dashboard in to Indent dashboard | TMS Dashboard | TMS Dashboard | Taseen Sir | Done | 2025-09-25
69 | Direct download report is not working | Slot wise | Bluedart | Mehdi | Done | 2025-09-08
70 | Route type coloum is not showing in trigger report | Trigger Report | Bluedart | Saumya | Done | 2025-09-22
71 | Trip Closed but but trip status & ATA is not updated ( Manual closer) | Trip Dashboard | DHL | Mayank /Mehdi | Done | 2025-09-26 |  | 1
72 | Portalbe Elock count is incorrcet in trip dashboard pie chart | Trip Dashboard | DHL | Mayank /Mehdi | Done | 2025-09-26 |  | 1
73 | Redirected button (Trip dashboard & irun dashboard) not working | CCH Dashboard | Bluedart | Sanvi | Done | 2025-11-13
74 | No data showing in distance report in Trasnporter login | Report | CV | Mehdi | Done | 2025-09-25
75 | dropdown value attached with search box are moving during the page scroll | CCH Dashboard | Bluedart | Sanvi | Done | 2025-11-13
76 | While click on alert flag Alert start time and end time are not showing | Irun | DHL |  | Done | 2025-09-27 |  | 1
77 | Region name & Location name are not showing in slot wise report | Slot wise | DHL | Mehdi | Done | 2025-09-27 |  | 1
78 | Route fleet assignment: | Route Fleet | DHL |  | Done | 2025-11-09
79 | Vehicle location is incorrcet if we assigne same vehicle with two customer | Vehicle report | DHL | Saumya | Done | 2025-09-26 |  | 1
80 | Vehicle listing are not showing in vehicle report | Vehicle report | DHL | Mustakeen / saumya | Done | 2025-09-26 |  | 1
81 | Incorrect location showing in vehicle (PB1D5196) | Vehicle report | DHL | Mustakeen / saumya | Done | 2025-09-26 |  | 1
82 | Vehile list are not showing Doucment wallet | Doucment Wallet | DHL_TMS | Mehdi | Done | 2025-09-27
83 | Input text font sizes are too large. Keep them under text box size. | Route Fleet | DHL |  | Done | 2025-11-09
84 | While uploading the document on the trip, the pop-up page is not working | Irun | DHL | Mehdi | Done | 2025-09-27 |  | 1
85 | Driver Dashboar layout is not looking good (Transporter login ) | Driver Dashboard | DHL_TMS | Mehdi | Done | 2025-09-27
86 | No Vehicle is showing Vehicle near by | Driver Dashboard | DHL_TMS | Mehdi | Done | 2025-09-27
87 | Driver dashboard page is not working in transporter login | Driver Dashboard | DHL_TMS | Mehdi | Done | 2025-09-27
88 | Destination is showing blanck | Irun | DHL |  | Done | 2025-11-08
89 | Alert Summay should be dispaly if no alert is open | Irun | DHL |  | Done | 2025-09-27 |  | 1
90 | trip successfully converted into a high-value message display while convert the HPT but not display in irun Dashboard | Irun | DHL | Mehdi | Done | 2025-09-27 |  | 1
91 | Alert report are not generating | Irun | DHL |  | Done | 2025-09-27 |  | 1
92 | M1 M2 location marker is not showing showing | Irun/ trip dasboard | DHL |  | Done | 2025-09-27 |  | 1
93 | 4. In location sequence font size too large. | Route Fleet | DHL |  | Done | 2025-11-09
94 | Fleet coloum Missing in Excel | Route fleet | TMS | Saumya | Done | 2025-09-25 | 2025-09-26
95 | By Default table shoud be display | Route fleet | TMS | Saumya | Done | 2025-09-25 | 2025-09-25
96 | 6. Sometimes location suggestions are not available in drop down. | Route Fleet | DHL |  | Done | 2025-11-09
97 | Trasnporter dashboard data is showing blank in card grap | Transporter Dashboard | CV | Mehdi | Done | 2025-09-25
98 | 0 | All New Pages | TMS | Mehdi | Done | 2025-09-08
99 | Transporter dashboard (card) layout is not correct | Transporter login | TMS | Mehdi | Done | 2025-09-03
100 | Same Pan No is not accept while registration in user Register any other account | Transporter Onboarding | DHL_TMS | Mehdi | Done | 2025-09-27
101 | Trip dashboard page is not working if we select all type feeder | Trip Dashboard | Bluedart | Mehdi | Done | 2025-09-22
102 | Supervisor Exception Colum is showing Blank in Trip report. | Trip report | Bluedart | Saumya /Taseen Sir | Done | 2025-09-25
103 | System remarks is showing invalid Vaule | Trip report | Bluedart | Saumya /Taseen Sir | Done | 2025-09-25
104 | Some Vehicle trip not visible in Region login (MH46CL6014) | Trip report / Trip Dashboard | Bluedart | Taseen Sir | Done | 2025-09-20
105 | While Search vehile same vehicle show entry in 2 times | Vehicle near by | Bluedart | Saumya | Done | 2025-09-22
106 | Unable to Download Vehicle report | Vehicle Report | Bluedart | Mustakeen / saumya | Done | 2025-09-08
107 | Unable to add a vehicle. After filling the form and clicking Submit, No data is showing . (Transporter login ) | Vehicle dashboard | DHL_TMS | Mehdi | Done | 2025-09-27
108 | GPS Vendor, Transporter filter is not working | Trip Dashboard | DHL | Mehdi | Done | 2025-09-26 |  | 1
109 | Trip closed by geofence but trip status are still showing running. | Trip Dashboard | DHL |  | Done | 2025-10-12 |  | 1
110 | 7. If the user continues to click on backspace then the selected locations are removed. That should be only when the user clicks on the X icon available in individual locations. | Route Fleet | DHL |  | Done | 2025-11-09
111 | 9. Need to add the option to add fleet timing in hours along with minutes. | Route Fleet | DHL |  | Done | 2025-11-09
112 | M1, M2 customer flag is not showing in tracking | Trip report | DHL | Saumya | Done | 2025-09-26 |  | 1
113 | Aler Name coloum is not showing in chart | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-18
114 | After Approved the transporter appoval email is received but staus are still showing pending | Transporter Onboarding | DHL_TMS | Mehdi | Done | 2025-09-27
115 | While click on trip dashboard , and irun dashboard No data is display | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-18
116 | Filter not working | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-10-22
117 | Session Logout Error Message not Showing.Loding page goes to Hang. | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-22
118 | 2. Iran and Trip dashboard link is not working. URL get data method is not passing properly | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-22
119 | 3. Graph data showing Incorrect. Total value must be Unattended + attended | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-22
120 | 4. Graph is not userfriendly. To show top 5 alert Total Count in Graph. | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-22
121 | 5. Table alignment is not properly adjusted | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-22
122 | 6. Link Heading is not user friendly. | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-22
123 | Top Heading is simple and is not matched with layout. | CCO Dashboard | Bluedart | Sanvi | Done | 2025-10-22
124 | Graph name is not accurate | CCH Dashboard | Bluedart | Sanvi | Done | 2025-11-13
125 | after filter selection. Submit button shifted downward | CCH Dashboard | Bluedart | Sanvi | Done | 2025-11-13
126 | Side Menu is not showing on new tab when pages open in Angular 18 | Call Center | Bluedart | Sanvi | Done | 2025-10-22
127 | Billing Modudle page is not showing in Transporte login | Billing | DHL_TMS | Taseen Sir | Done | 2025-09-27
128 | Empty Data of Iran hangs or showing loading | CCH Dashboard | Bluedart | Sanvi | Done | 2025-10-22
129 | Executive list fetching too slow | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
130 | GPS Vendor, vehicle filter is not working | Trip report | DHL | Saumya | Done | 2025-09-26 |  | 1
131 | Unable to add a vehicle. After filling the form and clicking Submit, only a processing window is shown. (Transporter login ) | Vehicle Dashboard | DHL_TMS | Mehdi | Done | 2025-09-27
132 | Vehicle dashboard page is not working in transporter login | Vehicle Dashboard | DHL_TMS | Mehdi | Done | 2025-09-27
133 | While click on view map unable to get loction once GPS is active | Vehicle near by | DHL_TMS | Mehdi | Done | 2025-09-25
134 | total column & row are missing in unattended alert statistics | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
135 | Unable to delete roaster | Call Center Attendance ( Roaster) | Bluedart |  | Done | 2025-11-08
136 | In route code after starting typing route all suggestions should come. Currently it work as when we start typing nothing looks available in master but when completed suddenly it starts appearing. | Route Fleet | DHL |  | Done | 2025-11-09
137 | 12. All days and location information is not captured in the database. | Route Fleet | DHL |  | Done | 2025-11-09
138 | 5. In location sequence when user type and select the associated location even after that type entry is not removed and if continue to type another location it considers the previous typing too. So when the user selects a location in drop down the text typed should be auto-disappear. | Route Fleet | DHL |  | Done | 2025-11-09
139 | 13. The View details option is not working. | Route Fleet | DHL |  | Done | 2025-11-09
140 | 14. Many fields like create date, days data is missed in route fleet listings. | Route Fleet | DHL |  | Done | 2025-11-09 |  |  | Days is missing
141 | Vehicle no filter is not available | Slot wise | DHL | Mehdi | Done | 2025-09-27 |  | 1
142 | 10. In fleet timing details those fields that are restricted to input anything should be highlighted differently like disable. | Route Fleet | DHL |  | Done | 2025-11-09
143 | 11. If the user enters the shortcut timing then the system should auto capture the duration. Ex if the user enters 06 only then the system should auto be considered as 06:00. | Route Fleet | DHL |  | Done | 2025-11-09
144 | Need to be add gps vendor filter | Slot wise | DHL | Mehdi | Done | 2025-09-27 |  | 1
145 | M1, M2 is not showing in Summary dashboard once we track on vehicle after click of Hyperlink | Summary Dashboard / trip report | DHL | Mehdi | Done | 2025-09-26 |  | 1
146 | While click on + icon no data is display in trip dashboard and trip report | Trip Dashboard | DHL |  | Done | 2025-10-12 |  | 1
147 | Trip Id Coloum & STD or ATD Coloum is showing Blank | Trip dashboard | DHL | Mehdi | Done | 2025-11-07 |  | 1
148 | Free Vehicle , At sourec , at destination count is incorrect | Trip Dashboard | DHL | Mehdi | Done | 2025-09-26 |  | 1
149 | Vehicle near by page is not working | Vehicle near by | DHL |  | Done | 2025-11-12
150 | Shift filter not working | CCH Dashboard | Bluedart | Sanvi | Done | 2025-11-13
151 | Geofence landmark are showing in home page | Home Page | Bluedart | Saumya | Done | 2025-09-22
152 | Graph color is not same as ppt | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
153 | Graph name is not accurate | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
154 | Employee name & Alert excelation should be freeze while vertical scroll | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
155 | incomplete name should display in mousehover | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
156 | Irun dashboard not working | CCH Dashboard | Bluedart | Sanvi | Done | 2025-11-13
157 | Filter is working too slow | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
158 | Unattend alert count not matching | CCH Dashboard | Bluedart | Sanvi | Done | 2025-11-14
159 | Session Expire message is not showing | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-10-22
160 | Landing page should be "CCTL Dashboard" | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
161 | By default should show data for current date | CCTL Performance Dashboard | Bluedart | Sanvi | Done | 2025-11-12
162 | unable to generate the report | Employee Performance Report | Bluedart | Sanvi | Done | 2025-11-12
163 | Unable to copy any text | Halt Report | Bluedart | Saumay | Done | 2025-10-11
164 | Filter is not working | Route fleet | Bluedart | Mehdi | Done | 2025-11-13
165 | While Assigne the vehicle Trip Source & destination are showing blank | Route fleet | Bluedart | Mehdi | Done | 2025-11-13
166 | Alert statistics graph count is not correct | CCH Performance Dashboard | Bluedart | Sanvi | Done | 2025-11-14
167 | Branch name not be mandory | Route fleet | Bluedart | Mehdi | Done | 2025-11-13
168 | Alert statistics table total count is not correct | CCH Performance Dashboard | Bluedart | Sanvi | Done | 2025-11-14
169 | there is no option to assign the vehicle in customer login | Route fleet | Bluedart | Mehdi | Done | 2025-11-13
170 | After assign the fleet details to trasnporter not refrlecting in transporter account | Route fleet | Bluedart | Mehdi | Done | 2025-11-13
171 | Graph look is not good. Spread widely | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
172 | dropdown value attached with search box are moving during the page scroll | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
173 | dropdown value attached with search box are moving during the page scroll | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-13
174 | got the API Error after session time out. Message should be display as session time out (msg Display) | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-13
175 | after filter selection. Submit button shifted downward | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-13
176 | Irun dashboard not working | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-13
177 | in CCTL Dashboard, Side Menu is not available | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
178 | Top performer TL popup reportcount is not matching | CCH performance Dashboard | Bluedart | Sanvi | Done | 2025-11-25
179 | Roaster, Trip dashboard, IRUN Dashboard. On click redirected option not available | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
180 | upon redirected to irun dashboard, data not available | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-14
181 | Shift filter not working | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
182 | after session time out & new login. CCTL Dashboard show error "session expired due to new login". | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-12
183 | Graph look is not good. Spread widely | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-13
184 | Roaster, Trip dashboard, IRUN Dashboard. On click redirected option not available | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-13
185 | chart count alert no is not correct | CCTL Performance Dashboard | Bluedart | Sanvi | Done | 2025-11-12
186 | Shift filter not working | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-13
187 | after session time out & new login. CCTL Dashboard show error "session expired due to new login". | CCTL Dashboard | Bluedart | Sanvi | Done | 2025-11-13
188 | Alert statistics graph count is not correct | CCTL Performance Dashboard | Bluedart | Sanvi | Done | 2025-11-14
189 | Executive roaster popup report is not available | CCH performance Dashboard | Bluedart | Sanvi | Done | 2025-11-14
190 | Top performer CCO popup report is not available | CCH performance Dashboard | Bluedart | Sanvi | Done | 2025-11-14
191 | Top performer TL popup report is not available | CCH performance Dashboard | Bluedart | Sanvi | Done | 2025-11-14
192 | Alert statistics table total count is not correct | CCTL Performance Dashboard | Bluedart | Sanvi | Done | 2025-11-14
193 | Cell ID tracking is not showing | DHL | DHL | Pawan / mehdi/ | Done | 2025-11-19
194 | Onboarding not showing in indenting | Indent | TMS_Xiomi | Medhi | Done | 2025-11-12
195 | Executive roaster popup report is not available | CCTL Performance Dashboard | Bluedart | Sanvi | Done | 2025-11-14
196 | Top performer CCO popup report is not available | CCTL Performance Dashboard | Bluedart | Sanvi | Done | 2025-11-14
197 | Distance travel is incorrect in all risk score vehicle | RiSk Score | CV | Mustaqeem | Done | 2025-11-07
198 | Internal transporter listing is not showing | Route Schedular | Bluedart | Mehdi | Done | 2025-11-13
199 | Serch option is not working | Route Schedular | Bluedart | Mehdi/ Mayank | Done | 2025-11-21
200 | While updating a new entry, the departure time is not updated in fleet assignment. | Route Fleet | Bluedart | Saumya/ Taseen sir | Done | 2025-12-04
201 | Filter is not working properly - Route fleet | Route Schedular | Bluedart | Mehdi/ Mayank | Done | 2025-11-21
202 | Apply cv2 portal menu in cv 18 |  | TMS_Xiomi | Medhi | Done | 2025-11-12
203 | Location is showing blank in some coloum | Route fleet | Bluedart | Saumya | Done | 2025-11-14
204 | Filter is not working properly - Route Schedule | Route Schedular | Bluedart | Mehdi/ Mayank | Done | 2025-11-21
205 | Fleet status is not update once Vehicle is on trip | Route Schedular | Bluedart | Mehdi/ Mayank | Done | 2025-11-21
206 | Sesson expier msg not Display | Route Schedular | Bluedart | Mehdi/ Mayank | Done | 2025-11-21
207 | After assigning the vendor, there is no option available for the customer to assign the vehicle. | Route Scheduler | Bluedart | Mehdi/mayank | Done | 2025-12-04
208 | Add a display message if no data is available within the selected date range. | Route Scheduler | Bluedart | Mehdi/mayank | Done | 2025-12-04
209 | Once we add a new fleet, it does not appear in the route scheduler if more than one days. | Route Scheduler | Bluedart | Mehdi/mayank | Done | 2025-12-04
210 | device use in trip id 15 but reflecting only 1 device in trip Report. | Trip report | Xiome | Saumya / Taseen Sir | Done | 2025-11-25
211 | VAS Count Display NULL in Graph | Master cv | IL | Mehdi | Done | 2025-11-21
212 | The Action and Status columns should be freez. | Route Scheduler | Bluedart | Mehdi/mayank | Done | 2025-12-04
213 | Total column count is inot showing in downlaod excel file | CCTL Performance Dashboard | Bluedart | Sanvi | Done | 2025-11-25
214 | Tentative Duration and Departure Time are showing as blank. | Route Scheduler | Bluedart | Mehdi/mayank | Done | 2025-12-04
215 | while login the transporter page is login balnk (tranporter trough registration) | Transporter Login | TMS_Xiomi | Medhi | Done | 2025-11-12
216 | some trips has been closed but trip alert are showing open | Trigger Report | Bluedart | Saumya / Mayank | testing pending | 2025-09-22
217 | Trip Status in not updated in some trip | Trigger Report Irun | Bluedart | Mehdi | testing pending | 2025-09-22
218 | ATD time capure incorrect in trip (Trip id )10400294 | Trip Report | Bluedart | Arpit | Done | 2025-11-21
219 | Cell ID tracking is not working on the Xiaomi trip report page. | Trip report | Xiome | Saumya/ Taseen sir | Done | 2025-12-04
220 | if vehcile added in Trough transporter master login not display in xiomin master account | Vehicle dashboard / trip creation Page / | TMS_Xiomi | Medhi | Done | 2025-11-12
221 | Calender should be auto hide | Lock report | DHL | Mehdi | Done | 2025-12-06
222 | if fleet cancelled by transporter then nedd to add option in customer login to assigne the tranporte any othe transporter | Route fleet | Bluedart | Mehdi | Done | 2025-12-09
223 | After assign the transporter customer unable to assign Vehicle | Route fleet | Bluedart | Mehdi | Done | 2025-12-09
224 | IMEI Not capture in many trips | Trip report | Bluedart | Deepankar/ Taseen sir | Done | 2025-12-10
225 | Area location & STD location date and time is showing is blank | Bluedart | Bluedart | Deepankar/ Taseen sir | Done | 2025-12-15
226 | As per the Route fleet .assignment the schedule depart Time is 14:00:00 HRS but in route scheduler it's reflecting 06:00:00 HRS | Route fleet | Bluedart | Mehdi | Done | 2025-12-09
227 | If the vehicle already assigend by Customer shoul be auto reflect in Trasnporte login | Route fleet | Bluedart | Mehdi | Done | 2025-12-09
228 | Trip Status in not updated | Route fleet | Bluedart | Mehdi | Done | 2025-12-09
229 | Unable to Download 1 month Bluedart Trip Report | Trip report | Bluedart | Taseen Sir / Mehdi | Pending | 2025-12-24
230 | While Search the Vehicle Serch Content not hide after Select the vehicle | Slot wise | Bluedart | Mehdi | Closed | 2026-01-03
231 | Region Shoul be Auto Select in Region type login | Slot wise | Bluedart | Mehdi | Closed | 2026-01-03
232 | Address coloum is missing while download the excel | Slot wise | Bluedart | Mehdi | Closed | 2026-01-03
233 | Same Vehicle entry are showing in two time in slow wise report (DL01LAA7338 1to 31 Dec 2025) | Slot wise | Bluedart | Mehdi | Pending | 2026-01-03
234 | Polygon Geofence not use in Alert Generation | Backend | Bluedart | Mayank | TBD | 2026-01-07
235 | Unable to Direct download one day trip report | Trip Report | Bluedart | Taseen sir/ Mehdi | Closed | 2026-01-07
236 | No opton availabe to download direct Details CSV report | Slot wise | Bluedart | Taseen sir/ Mehdi | Pending | 2026-01-07
237 | Some time Itraceit Portal is working slow | Portal | Bluedart | Rizwan Sir/ Taseen Sir | Pending | 2026-01-07
238 | Daywise detailed report view option not available in slotwise distance report | Slot wise | Bluedart | Mehdi | Pending | 2026-01-03
239 | ATD time capture incorrect in Many trips (10691533) due to polygon issue | Trip report | Bluedart | Mehdi | Done | 2026-01-03
240 | Unable to add route fleet in Bluedart login. It shows a message saying "already exists," but it does not display on the portal | Route Fleet | Bluedart | Taseen sir | Closed | 2026-01-03
241 | Working days should be billed specified range of days. | Billing | Bluedart |  | Closed
242 | Agreement should not be uploaded without fill vehicle details. | Billing | Bluedart | Mehdi | Pending | 2026-02-01
243 | The final distance field is missing. | Billing | Bluedart |  | Closed | 2026-02-01
244 | Fixed rent should display two decimal places. | Billing | Bluedart |  | Closed
245 | Fuel surcharge is not calculated for negative amounts. | Billing | Bluedart |  | Closed
246 | add a column for the total cost field. | Billing | Bluedart |  | Closed
247 | Unable to verifly bill | Billing | Bluedart | Mehdi | Closed | 2026-02-11
248 | Home Vehile page is working slow | Billing | Bluedart | Mehdi | Pending | 2026-02-11
249 | Vehicle search search option is not working in Vehicle utilization report | Vehicle utilization report | Bluedart | Mehdi | Pending | 2026-02-13
250 | Vehicle running filter count is incorrcet | Trip Dashboard | Bluedart | Mehdi | Pending | 2026-02-13
251 | DFG Alert is not log | Irun dashhboard | Bluedart | Mayank | Done | 2026-02-13
252 | Trip Dashboard and iRun Dashboard, the trip is shown as a circle, but in the Trip Report the same trip appears as a polygon | Trip Dashboard | Bluedart | Mayank | Pending | 2026-02-20
253 | Halt flag and halt report are not showing for 3rd party vehicle | Halt Report | Bluedart | Taseen sir/ Saumya | Done | 2026-03-03
254 | many alerts are closed but the “Closed User Name” field is blank, | Halt Report | Bluedart | Saumya | Pending | 2026-03-03
255 | Once we click on the Vehicle Count hyperlink in summary Dasboard Page, the system automatically logs out. | Summary Dashboard | Bluedart | Saumya | Done | 2026-03-03
256 | total vehicle count, active trip count, and inactive trip count shown in the Bluedart Summary Dashboard are showing to be incorrect. | Summary Dashboard | Bluedart | Saumay / Taseen sir | Pending | 2026-03-16
257 | Once we click Summary dashboard trip Some Coloum (FixedGpsKm FixedELockKm PortableELockKm GpsException1 GpsException2 GpsException3 ) is missing. Please add the same in report | Summary Dashboard | Bluedart | Saumay / Taseen sir | Pending | 2026-03-17
258 | 1.Device is not assigned, but it is still showing in the account. | Assest mananment | Bluedart | Mayank / Saumya/ Mehdi/ taseen sir | Done | 2026-03-23
259 | 2.If the last status is open, the lock icon should appear open,currently it show closed | Assest mananment | Bluedart | Mayank / Saumya/ Mehdi/ taseen sir | Done | 2026-03-23
260 | 3.When clicking on the table action icon, the entire page automatically refreshes. | Assest mananment | Bluedart | Mayank / Saumya/ Mehdi/ taseen sir | Done | 2026-03-23
261 | 4.The lock status and lock last data is incorrcet (860181061720808 ) | Assest mananment | Bluedart | Mayank / Saumya/ Mehdi/ taseen sir | Done | 2026-03-23
262 | 5.Lock status icon is incorrcet. | Assest mananment | Bluedart | Mayank / Saumya/ Mehdi/ taseen sir | Done | 2026-03-23
263 | 6.Lock Status pie chart showing incorrcet | Assest mananment | Bluedart | Mayank / Saumya/ Mehdi/ taseen sir | Done | 2026-03-23
264 | 7.Device pie chartlocation is incorrect | Assest mananment | Bluedart | Mayank / Saumya/ Mehdi/ taseen sir | Done | 2026-03-23
265 | 8.Device pie chart Location is incorrect | Assest mananment | Bluedart | Mayank / Saumya/ Mehdi/ taseen sir | Done | 2026-03-23
266 | Location in / out time are showing blank in transporter login ( | Slot wisereport | Bluedart | Saumay / Taseen sir | Pending | 2026-03-26
267 | Potable Device are showinh Transporter login. | Slot wisereport | Bluedart | Saumay / Taseen sir | Closed | 2026-03-26
268 | AMH to KSW trip is not showing in north . once AMH locations is assigned with not region. | Trip dahborad | Bluedart | Saumay / Taseen sir | Done | 2026-03-27
269 | Some trips are not showing in region login | Trip dahborad | Bluedart | Saumay / Taseen sir | Closed | 2026-03-30
270 | Lock status count is incorrcet in pie chat | Assest mananment | Bluedart | Mehdi / Mayank | Pending | 2026-04-09
271 | Trip id Coloum Is showing blank | Assest mananment | Bluedart | Mehdi / Mayank | Pending | 2026-04-09
272 | When clicking on mapped location flags (M1, M2) is not showing | Assest mananment | Bluedart | Mehdi / Mayank | Pending | 2026-04-09
273 | Tracking Download option is misiing | Assest mananment | Bluedart | Mehdi / Mayank | Pending | 2026-04-09
274 | when clicking on a tracking bubble (map marker),all information should be display( Same as trip dashboard) | Assest mananment | Bluedart | Mehdi / Mayank | Pending | 2026-04-09
275 | Battery coloum Values show as percentages and colour (50% – 100% - Green) , (20% – 49% Yellow) ,( 0% – 20%- Red ) | Assest mananment | Bluedart | Mehdi / Mayank | Pending | 2026-04-09
| Portable Device lock report are not showing | Lock report | Bluedart | Mehdi / Mayank | Pending

## Sheet4
SN | Point | Page | Account | Owner
Run date and time Should be Diffren coloum
Date Formar DD:MM:YY
QRT Login
Dashhcam POC for Bluedart
Lock POC for Bluedart
Dashcam Poratl
Asseset management Portal
Itaceit new trail api shoule Be live
Itrace login page Layout need to be update
Lock report need be add
Transporter report

## DHL Login
Account Type | Group | Username | Password
Master | DHL (5864) | dhl_master | Dhl@2025
Admin | DHL (5864) | dhl_admin | Dhl@2025admin
Corporate Manager | DHL (5864) | testdhl | Dhl@2025
Transporter | DHL (5864) | tejas | Tejas@2025
Master Login:
Group ID: 5865
Username: TejasCargoIndiaLtd_master
Password: Salman@123
Admin Login:
Username: TejasCargoIndiaLtd_admin
Password: Q0BW(%C_
alert_closeby
Rushikesh Jadhav(0770) | 770 | Rushikesh Jadhav | rushikesh | Rushikesh@2025
Priti Deshmukh(0770) | 770 | Priti Deshmukh | priti | Priti@2025
Suneet Khilare(0770) | 770 | Suneet Khilare | suneet | Suneet@2025
Nikita Dande(0770) | 770 | Nikita Dande | nikita | Nikita@2025

## CCO login
SI | User Type | Name | Mobile No. | Email ID | Gropu id | User ID | Password | TL | Punch in
1 | CCO | Atharva Inamdar | 7020387914 | atharvainamdar.cds@gmail.com | 770 | Atharva | Atharva@2025
2 | CCO | Imran Khan | 8482916407 | imrankhan.cds0@gmail.com | 770 | Imran | Imran@2025
3 | CCO | Pooja Anarase | 9766612994 | poojaanaras.cds@gmail.com | 770 | pooja | Pooja@2025
4 | CCO | Pravin Shelke | 7058236035 | pravinshelke.cds@gmail.com | 770 | pravin | Pravin@2025
5 | CCO | Rasika Joshi | 83083 37706 | rasikajoshi.cds@gmail.com | 770 | rasika | Rasika@2025
6 | CCO | Rohit Kangune | 70388 10610 | rohitkangune.cds@gmail.com | 770 | rohit | Rohit@2025
7 | CCO | Saurabh Rodge | 7875798746 | sourabhrodge.cds@gmail.com | 770 | saurabh | Saurabh@2025
8 | CCO | Shreya Alandkar | 7820932959 | shreyacharter.cds@gmail.com | 770 | shreya | Shreya@2025 | ctr_Test1_CCTL | 15:54
9 | CCO | Shubham Patil | 9851680789 | shubhampatil.cds@gmail.com | 770 | shubham | Shubham@2025
10 | CCO | Tejas Tigote | 95271 13394 | tejas.cds@gmail.com | 770 | tejas | Tejas@2025
11 | CCO | Vivek Randhir | 91456 88208 | vivekrandhir.cds@gmail.com | 770 | vivek | Vivek@2025 | ctr_Test1_CCTL | dd
12 | CCH |  |  |  |  | ctr_Test_CCH | Test@123
13 | CCTL |  |  |  |  | ctr_Test1_CCTL | Test@123 | Shreya Alandkar | Vivek Randhir | Rushikesh Jadhav
14 | CCTL |  |  |  |  | ctr_Test2_CCTL | Test@123 | Rasika Joshi | Priti Deshmukh | Suneet Khilare
15 | CCTL |  |  |  |  | ctr_Test3_CCTL | Test@123 | Imran Khan | Pooja Anarase
16 | Master Account |  |  |  |  | charter_master | Charter_master@2025

## Xiaomi
Group Name:Xiaomi
Group ID:5884
Master Account
User Name:xiaomi
Password:Xiaomi@2025
Admin Account
User Name:xiaomi_admin
Password:Xiaomi@2025
Manager Account
User Name:xm_manager
Password:Xiaomi@2025

## Sheet1
Sr. No | Issue | HO Cordinator | Remarks
1 | Need To Create management Dashboard Summary | Dipak | Pending from Bde end
2 | While creating trip there should be option to mark trip as high value /Electronic shipment | Vishram | Pending | Will do later
3 | Need to have 1 Vehicles wise report where 0 ping generated in last 7 days | Nitin | Done
4 | ATD is Blank even if there is gps in vehicles | Nitin | Pending from Bde end
5 | RNCC Login Location wise | Vishram | Pending from Bde end
6 | Sector Delay Logic Issue | Nitin | Bug | Bug | Mayank
7 | Geofence right to be activated to NCC master login | Nitin | Done
8 | SFC Intra / Inter option required in NCC login | Vishram | Pending |  | 2
9 | Need 3 options in shipment method | Vishram | Layout Issue , already discussed
10 | RNCC Login -Toggle switch / filter required for Inter / Intra ( Intra is selected by default) | Vishram | Pending | Filter for Inter / Intra | 2 | Saumya / Taseen Sir
11 | Only one RNCC ID available currently – need two separate logins | Vishram | Pending from Bde end
12 | RR500 Alerts need to be checked – verify working status & logic | Vishram | Done
13 | RNCC Login .Delay Dashboard :- Toggle switch / filter required for IN | Vishram | Pending | Filter for Inter / Intra | 2 | Saumya / Taseen Sir
14 | Need Mobile App dashboard demo if available | Nitin | Pending from Bde end
15 | Vehicle breakdown / Offroad report need to be concluded | Vishram | Pending
16 | India map view or vehicles | Dipak | Pending |  | 1 | Saumya
17 | Team leader dashboard | Dipak | Pending from Bde end
18 | Need to remove unwanted icon from irun dashboard | Dipak | Done |  | 1 | Saumya
19 | Need to remove driver and vehicle dashboard if not in use | Dipak | no need to remove |  | 1 | Saumya
20 | Sensitive alert filtering | Nitin | Done |  |  | Salman to check
21 | Route Template should replicate in Itraceit, if it changed/modified in TMS | Nitin | Pending from Bde end
22 | Multiple users for RNCC in single login | Nitin | Pending from Bde end
23 | Need Stoppages Details based on 15 Mins/30mins/45mins/1hrs ( fleet-x screenshot shared by self | Dipak | Pending from Bde end
24 | In Vehicle Nearby Options, Highlight the filtered Vehicle with red color and Plot nearby BD locations as well to identify nearest location till 100 KM | Dipak | Done
25 | Poratble lock count symbol in Tamper lock if any | Dipak | TBD With Bde team |  | 1 | Taseen sir
26 | Multiple users for RNCC in single login… | Vinayak | Not Possible due to Security Concern |  | 1 | Security Concern
27 | Multiple Geo fence creation under same location ,so that auto closer can be taken place | Vinayak | Done |  |  | Already have
28 | TMS to Location geo fence sharing in Itraceit app(In real Time) | Vinayak | Pending from Bde end
29 | ICICI backed team close ATA ,manually without ATA Time,this need to be restricted for Surface,Air network,Speed network//Without Actual Arrival time they should not close trip in Itraceit app. | Vinayak | Pending from Bde end
30 | User selecting wrong Feeder type ,this need to restrict it should be based on TMS master based on Route-Run Type-Route sequence in master no manual updation allowed | Vinayak | TBD With Bde team
Closeing time restirtc 1 hours

## Sheet2
Sr. No | Issue | HO Cordinator | Due Date | Remarks
1 | Need To Create management Dashboard Summary | Dipak
2 | While creating trip there should be option to mark trip as high value /Electronic shipment | Vishram | 10th March
3 | Need to have 1 Vehicles wise report where 0 ping generated in last 7 days | Nitin | 10th March
4 | ATD is Blank even if there is gps in vehicles | Nitin | 25th Feb | BD to Share the case
5 | RNCC Login Location wise | Vishram | 28th Feb
6 | Sector Delay Logic Issue | Nitin | Closed
7 | Geofence right to be activated to NCC master login | Nitin | 25th Feb | Need to be share Login Credetails
8 | SFC Intra / Inter option required in NCC login | Vishram | 10th March
9 | Need 3 options in shipment method | Vishram | Need to Discuss
10 | RNCC Login -Toggle switch / filter required for Inter / Intra ( Intra is selected by default) | Vishram | 10th March
11 | Only one RNCC ID available currently – need two separate logins | Vishram | 25th Feb | Login User Details to be shared by BD
12 | RR500 Alerts need to be checked – verify working status & logic | Vishram | 25th Feb | BD to Ask 1 vendor to go behind 5 km
13 | RNCC Login .Delay Dashboard :- Toggle switch / filter required for IN | Vishram | 10th March
14 | Need Mobile App dashboard demo if available | Nitin | Need to Discuss
15 | Vehicle breakdown / Offroad report need to be concluded | Vishram/Nitin | 28th Feb | Currently Alert should come,BD will confirm next course of action
16 | India map view or vehicles | Dipak | 15th March
17 | Team leader dashboard | Dipak | NA | Can be discussed later
18 | Need to remove unwanted icon from irun dashboard | Dipak | Done
19 | Need to remove driver and vehicle dashboard if not in use | Dipak | NA
20 | Sensitive alert filtering | Nitin | 27th Feb
21 | Route Template should replicate in Itraceit, if it changed/modified in TMS | Nitin | NA | Pending from TMS
22 | Multiple users for RNCC in single login | Nitin
23 | Need Stoppages Details based on 15 Mins/30mins/45mins/1hrs ( fleet-x screenshot shared by self | Dipak | Done | We will disccus mumbai
24 | In Vehicle Nearby Options, Highlight the filtered Vehicle with red color and Plot nearby BD locations as well to identify nearest location till 100 KM | Dipak | Done | To be checked and confirm
25 | Poratble lock count symbol in Tamper lock if any | Dipak |  | We will disccus mumbai
26 | Multiple Geo fence creation under same location ,so that auto closer can be taken place | Vinayak | Done
27 | TMS to Location geo fence sharing in Itraceit app(In real Time) | Vinayak | NA
28 | ICICI backed team close ATA ,manually without ATA Time,this need to be restricted for Surface,Air network,Speed network//Without Actual Arrival time they should not close trip in Itraceit app. | Vinayak
29 | User selecting wrong Feeder type ,this need to restrict it should be based on TMS master based on Route-Run Type-Route sequence in master no manual updation allowed | Vinayak | 27th Feb | Vinayak to share one brd
30 | Complaint module not available in new Itraceit
31 | Region Was blank | Nitin | 24th Feb | Nitin to check trip report both
32 | Sim Based Tracking
33 | Himanshu/Samiran to share me the top 10 GPS vendors for API Integration
34 | Feeder run to be linked | Vishram |  | Vishram to take 2 or 3 Trips which are showing as feeder trip in IN ICICI

## Sheet3
Sr. No | Issue | HO Cordinator | Due Date | Remarks
1 | Need To Create management Dashboard Summary | Dipak
2 | While creating trip there should be option to mark trip as high value /Electronic shipment | Vishram | 10th March
3 | Need to have 1 Vehicles wise report where 0 ping generated in last 7 days | Nitin | 10th March
4 | ATD is Blank even if there is gps in vehicles | Nitin | 25th Feb | BD to Share the case
5 | RNCC Login Location wise | Vishram | 28th Feb
6 | Sector Delay Logic Issue | Nitin | OK
7 | Geofence right to be activated to NCC master login | Nitin | 25th Feb
8 | SFC Intra / Inter option required in NCC login | Vishram | 10th March
9 | Need 3 options in shipment method | Vishram | Need to Discuss
10 | RNCC Login -Toggle switch / filter required for Inter / Intra ( Intra is selected by default) | Vishram | 10th March
11 | Only one RNCC ID available currently – need two separate logins | Vishram | 25th Feb | Login User Details to be shared by BD
12 | RR500 Alerts need to be checked – verify working status & logic | Vishram | 25th Feb | BD to Ask 1 vendor to go behind 5 km
13 | RNCC Login .Delay Dashboard :- Toggle switch / filter required for IN | Vishram | 10th March
14 | Need Mobile App dashboard demo if available | Nitin | Need to Discuss
15 | Vehicle breakdown / Offroad report need to be concluded | Vishram/Nitin | 28th Feb | Currently Alert should come,BD will confirm next course of action
16 | India map view or vehicles | Dipak | 15th March
17 | Team leader dashboard | Dipak | NA | Can be discussed later
18 | Need to remove unwanted icon from irun dashboard | Dipak | NA
19 | Need to remove driver and vehicle dashboard if not in use | Dipak | NA
20 | Sensitive alert filtering | Nitin | 27th Feb
21 | Route Template should replicate in Itraceit, if it changed/modified in TMS | Nitin | NA | Pending from TMS
22 | Multiple users for RNCC in single login | Nitin
23 | Need Stoppages Details based on 15 Mins/30mins/45mins/1hrs ( fleet-x screenshot shared by self | Dipak |  | We will disccus mumbai
24 | In Vehicle Nearby Options, Highlight the filtered Vehicle with red color and Plot nearby BD locations as well to identify nearest location till 100 KM | Dipak | Closed | To be checked and confirm
25 | Poratble lock count symbol in Tamper lock if any | Dipak |  | We will disccus mumbai
26 | Multiple Geo fence creation under same location ,so that auto closer can be taken place | Vinayak | Done
27 | TMS to Location geo fence sharing in Itraceit app(In real Time) | Vinayak | Pending
28 | ICICI backed team close ATA ,manually without ATA Time,this need to be restricted for Surface,Air network,Speed network//Without Actual Arrival time they should not close trip in Itraceit app. | Vinayak
29 | User selecting wrong Feeder type ,this need to restrict it should be based on TMS master based on Route-Run Type-Route sequence in master no manual updation allowed | Vinayak | 27th Feb | Vinayak to share one brd
30 | Complaint module not available in new Itraceit
31 | Region Was blank | Nitin | 24th Feb | Nitin to check trip report both
32 | Sim Based Tracking
33 | Himanshu/Samiran to share me the top 10 GPS vendors for API Integration
34 | Feeder run to be linked | Vishram |  | Vishram to take 2 or 3 Trips which are showing as feeder trip in IN ICICI